{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["桩基报价"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"桩基报价","index":0,"n_rows":29,"n_cols":12,"rows_kept":29,"merged":[[0,0,0,11],[2,0,3,0],[2,1,3,1],[2,2,2,3],[2,4,3,4],[2,5,3,5],[2,6,3,6],[2,7,3,7],[2,8,3,8],[2,9,3,9],[2,10,3,10],[2,11,3,11],[4,0,7,0],[4,1,7,1],[4,2,7,2],[4,3,7,3],[4,4,7,4],[4,5,7,5],[8,0,11,0],[8,1,11,1],[8,2,11,2],[8,3,11,3],[8,4,11,4],[8,5,11,5],[12,0,21,0],[12,1,21,1],[12,2,13,2],[12,3,13,3],[12,4,13,4],[12,5,13,5],[14,2,15,2],[14,3,15,3],[14,4,15,4],[14,5,15,5],[16,2,21,2],[16,3,21,3],[16,4,21,4],[16,5,21,5],[22,0,24,0],[22,1,24,1],[22,2,24,2],[22,3,24,3],[22,4,24,4],[22,5,24,5],[27,0,27,5],[27,6,27,11],[28,0,28,11]],"flags":["formulas_cached_only"]}
["华东师范大学附属三明中学建设项目1#楼、2#楼及下穿通道和下沉广场地基基础检测工程量"]
["报价单位："]
["单位工程","桩径（mm）","桩数（根）",null,"抗压极限承载力（kN）","抗拔承载力特征值（kN）","检测内容","单位","检测数量","单价","金额","检测频率"]
[null,null,"抗压","抗拔"]
["1#教学楼、科技楼",900,276,110,10320,600,"工程桩单桩竖向抗压静载试验试验","根",3,null,null,"检测数量不小于总桩数的1%，且同条件下不小于3根。"]
[{"$nulls":6},"低应变检测","根",276,null,null,"全数检测。"]
[{"$nulls":6},"声波透射法检测","根",28,null,null,"检测数量不小于总桩数的10%。"]
[{"$nulls":6},"工程桩静载抗拔","根",3,null,null,"检测数量不小于总桩数的1%，且同条件下不小于3根。"]
["2#体育馆、食堂",900,215,46,10320,600,"工程桩单桩竖向抗压静载试验试验","根",3,null,null,"检测数量不小于总桩数的1%，且同条件下不小于3根。"]
[{"$nulls":6},"低应变检测","根",215,null,null,"全数检测。"]
[{"$nulls":6},"声波透射法检测","根",22,null,null,"检测数量不小于总桩数的10%。"]
[{"$nulls":6},"工程桩单桩竖向抗拔静载试验试验","根",2,null,null,"检测数量不小于总桩数的1%，且总桩数小于50根同条件下检测数量不小于2根。"]
["下穿通道支护桩",900,74,"/",2640,"/","高应变检测","根",5,null,null,"检测数量不小于总桩数的5%，且同条件下不小于5根。"]
[{"$nulls":6},"低应变检测","根",74,null,null,"全数检测。"]
[null,null,82,"/",2160,"/","高应变检测","根",5,null,null,"检测数量不小于总桩数的5%，且同条件下不小于5根。"]
[{"$nulls":6},"低应变","根",82,null,null,"全数检测。"]
[null,null,"/","/","/","/","钻孔取芯法","米",61,null,null,"依据设计说明检测数量不小于总桩数的0.5%，且不小于3根。"]
[{"$nulls":6},"载荷板试验","根",3,null,null,"单位工程检测数量不小于3点，每500㎡一个点。"]
[{"$nulls":6},"喷射混凝土面层厚度及强度","点",3,null,null,"每500m2试验数量1点，试验总量不少于3点。"]
[{"$nulls":6},"土钉基本试验","根",3,null,null,"试验数量为土钉总数的1%，且同一土层不小于3根。"]
[{"$nulls":6},"土钉验收试验","根",3,null,null,"试验数量为土钉总数的1%，且同一土层不小于3根。"]
[{"$nulls":6},"压实度（环刀法）","点",300,null,null,"依据设计说明每100㎡取一点，每层每段不小于1个点。"]
["基坑支护","/","/","/","/","/","土钉基本试验","根",3,null,null,"试验数量为土钉总数的1%，且同一土层不小于3根。"]
[{"$nulls":6},"土钉验收试验","根",3,null,null,"试验数量为土钉总数的1%，且同一土层不小于3根。"]
[{"$nulls":6},"喷射混凝土面层厚度及强度","点",13,null,null,"每500m2试验数量1点，试验总量不少于3点。"]
["设备进退场",{"$nulls":5},"设备进退场","趟",1,null,null,"进退场一次性费用"]
["其他","/","/","/","/","/","高应变专家论证费","/","/",null,null,"/"]
["合计（元）",{"$nulls":5},0]
["备注：①上述检测数量为暂定量，最终由委托方确定，按实结算；②静载抗压检测金额按承载力极限值1.2倍计算。"]